## Test Scenario
Project Name | Carwash IoT System | No | Function Name | Number Of TC | Description | Notes
Project Code | CAPSTONE-CARWASH-IOT | 1 | User Story 1 | 8 | Authentication & RBAC | Login, logout, role guard, inactive user
Test Environment Setup Description | Development / Localhost | 2 | User Story 2 | 5 | Dashboard | Summary cards and location based dashboard
|  | 3 | User Story 3 | 5 | Monitoring | Sensor status and live detection checks
|  | 4 | User Story 4 | 6 | Reports | Summary, PDF, Excel, audit exports
|  | 5 | User Story 5 | 6 | Sensor Management | Sensor CRUD and validation
|  | 6 | User Story 6 | 7 | User Management | RBAC user CRUD
|  | 7 | User Story 7 | 6 | Location Management | Location CRUD and capacity checks
|  | 8 | User Story 8 | 4 | Audit Logs | Trace login and CRUD events
|  | 9 | User Story 9 | 8 | IoT API Mock | Mock endpoint before real hardware integration

## Test Case
Module Code |  |  | CAPSTONE-CARWASH-IOT
Test requirement |  |  | Functional, Non Functional
Tester |  |  | Ricky
Results |  |  | Pass |  | Fail | Pending | Blocked | Invalid | Number of testcases
|  |  | 0 |  | 0 | 55 | 0 | 0 | 55
User Story | Date Tested | Module | ID TestCase | Scenario Type | Test Case Description | Precondition | Test Step | Expected Result | Status | Tester | Methode to use | Comments
User Story 1 | 2026-05-30 00:00:00 | Authentication & RBAC | TC_AUTH_001 | Positive | Owner login with valid credentials | Owner account exists and active | 1. Open login page. 2. Enter puji@carwash.test / puji123. 3. Click Login. | User is redirected to dashboard and owner menu is visible. | Pending | Ricky | Manual
User Story 1 | 2026-05-30 00:00:00 | Authentication & RBAC | TC_AUTH_002 | Positive | Admin login with valid credentials | Admin account exists and active | 1. Open login page. 2. Enter admin credential. 3. Click Login. | Admin is redirected to dashboard and can access operational menus. | Pending | Ricky | Manual
User Story 1 | 2026-05-30 00:00:00 | Authentication & RBAC | TC_AUTH_003 | Positive | Cashier login with valid credentials | Cashier account exists and active | 1. Open login page. 2. Enter cashier credential. 3. Click Login. | Cashier is redirected and restricted from owner/admin-only pages. | Pending | Ricky | Manual
User Story 1 | 2026-05-30 00:00:00 | Authentication & RBAC | TC_AUTH_004 | Negative | Login with wrong password | User is on login page | 1. Enter valid email. 2. Enter wrong password. 3. Click Login. | System rejects login and shows invalid credential message. | Pending | Ricky | Manual
User Story 1 | 2026-05-30 00:00:00 | Authentication & RBAC | TC_AUTH_005 | Negative | Login with blank required fields | User is on login page | 1. Leave email or password blank. 2. Click Login. | Form validation prevents login request or shows required field message. | Pending | Ricky | Manual
User Story 1 | 2026-05-30 00:00:00 | Authentication & RBAC | TC_AUTH_006 | Negative | Cashier opens Users page directly | Cashier is already logged in | 1. Navigate to /users from URL. | Access is denied or redirected according to role guard. | Pending | Ricky | Manual
User Story 1 | 2026-05-30 00:00:00 | Authentication & RBAC | TC_AUTH_007 | Positive | Logout from sidebar | User is logged in | 1. Click Logout button in sidebar. | Token is cleared and user returns to login page. | Pending | Ricky | Manual
User Story 1 | 2026-05-30 00:00:00 | Authentication & RBAC | TC_AUTH_008 | Negative | Inactive user cannot login | Inactive user exists in database | 1. Enter inactive user credential. 2. Click Login. | System blocks login and records failed audit event. | Pending | Ricky | Manual
User Story 2 | 2026-05-30 00:00:00 | Dashboard | TC_DASH_001 | Positive | Dashboard loads summary cards | Owner/Admin is logged in | 1. Open Dashboard. 2. Select active location. | Summary cards display total capacity, occupied slots, available slots, and sensor status. | Pending | Ricky | Manual
User Story 2 | 2026-05-30 00:00:00 | Dashboard | TC_DASH_002 | Positive | Location selector changes dashboard data | Multiple locations exist | 1. Change location from top selector. | Dashboard refreshes metrics for selected location only. | Pending | Ricky | Manual
User Story 2 | 2026-05-30 00:00:00 | Dashboard | TC_DASH_003 | Positive | Dashboard handles empty location | Location has no vehicle entries | 1. Select location without entries. | Dashboard displays zero counts without broken UI. | Pending | Ricky | Manual
User Story 2 | 2026-05-30 00:00:00 | Dashboard | TC_DASH_004 | Negative | Dashboard request without token | User token is missing/expired | 1. Clear token. 2. Open dashboard API/page. | System redirects to login or returns unauthorized response. | Pending | Ricky | Manual
User Story 2 | 2026-05-30 00:00:00 | Dashboard | TC_DASH_005 | Negative | Dashboard with invalid location id | User is logged in | 1. Request dashboard with invalid location_id. | System returns validation/not found response and UI remains stable. | Pending | Ricky | API/Manual
User Story 3 | 2026-05-30 00:00:00 | Monitoring | TC_MON_001 | Positive | Monitoring page displays active sensors | Sensor data exists | 1. Open Monitoring. | Sensor list/cards show latest status, distance, and occupancy state. | Pending | Ricky | Manual
User Story 3 | 2026-05-30 00:00:00 | Monitoring | TC_MON_002 | Positive | Monitoring follows selected location | Multiple locations/sensors exist | 1. Select another location. 2. Open Monitoring. | Only sensors from selected location are displayed. | Pending | Ricky | Manual
User Story 3 | 2026-05-30 00:00:00 | Monitoring | TC_MON_003 | Positive | Vehicle detection updates monitoring | Device key and sensor are valid | 1. Send valid vehicle detection payload to IoT endpoint. 2. Refresh Monitoring. | Sensor status/count reflects the new detection. | Pending | Ricky | API/Manual
User Story 3 | 2026-05-30 00:00:00 | Monitoring | TC_MON_004 | Negative | Inactive sensor payload is rejected | Sensor status is inactive | 1. Send vehicle detection payload for inactive sensor. | API rejects payload and no vehicle entry is created. | Pending | Ricky | API
User Story 3 | 2026-05-30 00:00:00 | Monitoring | TC_MON_005 | Negative | Duplicate device_event_id is rejected | Vehicle event already sent once | 1. Send same payload twice with same device_event_id. | Second request is rejected as duplicate. | Pending | Ricky | API
User Story 4 | 2026-05-30 00:00:00 | Reports | TC_REP_001 | Positive | Generate daily vehicle summary | Vehicle entries exist for selected date | 1. Open Reports. 2. Choose date range and location. 3. Generate summary. | Report table displays total vehicle count for selected filters. | Pending | Ricky | Manual
User Story 4 | 2026-05-30 00:00:00 | Reports | TC_REP_002 | Positive | Export vehicle summary PDF | Report filter is valid | 1. Click Export PDF. | Browser downloads PDF report successfully. | Pending | Ricky | Manual
User Story 4 | 2026-05-30 00:00:00 | Reports | TC_REP_003 | Positive | Export vehicle summary Excel | Report filter is valid | 1. Click Export Excel. | Browser downloads .xlsx report successfully. | Pending | Ricky | Manual
User Story 4 | 2026-05-30 00:00:00 | Reports | TC_REP_004 | Positive | Export audit log Excel | Owner/Admin is logged in | 1. Open Audit Logs or Reports export. 2. Export audit logs. | Audit log .xlsx file is downloaded. | Pending | Ricky | Manual
User Story 4 | 2026-05-30 00:00:00 | Reports | TC_REP_005 | Negative | Report start date after end date | User is on Reports page | 1. Set start date after end date. 2. Generate report. | System shows validation error and does not generate invalid report. | Pending | Ricky | Manual
User Story 4 | 2026-05-30 00:00:00 | Reports | TC_REP_006 | Negative | Cashier exports restricted report | Cashier is logged in | 1. Open restricted export endpoint/page. | System denies access based on role. | Pending | Ricky | Manual/API
User Story 5 | 2026-05-30 00:00:00 | Sensor Management | TC_SEN_001 | Positive | Create sensor | Owner/Admin is logged in and location exists | 1. Open Sensors. 2. Add sensor with unique code, location, threshold. 3. Save. | Sensor is created and appears in list. | Pending | Ricky | Manual
User Story 5 | 2026-05-30 00:00:00 | Sensor Management | TC_SEN_002 | Positive | Edit sensor threshold | Sensor exists | 1. Open sensor edit modal. 2. Change threshold. 3. Save. | Sensor data is updated and audit log is created. | Pending | Ricky | Manual
User Story 5 | 2026-05-30 00:00:00 | Sensor Management | TC_SEN_003 | Positive | Set sensor inactive | Sensor exists | 1. Edit sensor status to inactive. 2. Save. | Sensor status changes to inactive. | Pending | Ricky | Manual
User Story 5 | 2026-05-30 00:00:00 | Sensor Management | TC_SEN_004 | Negative | Create sensor with duplicate code | Sensor code already exists | 1. Add sensor using existing code. 2. Save. | System rejects duplicate code. | Pending | Ricky | Manual
User Story 5 | 2026-05-30 00:00:00 | Sensor Management | TC_SEN_005 | Negative | Create sensor with invalid threshold | Owner/Admin is logged in | 1. Input negative or non-numeric threshold. 2. Save. | Validation error is displayed. | Pending | Ricky | Manual
User Story 5 | 2026-05-30 00:00:00 | Sensor Management | TC_SEN_006 | Negative | Cashier accesses sensor management | Cashier is logged in | 1. Open Sensors page directly. | Access is denied or redirected. | Pending | Ricky | Manual
User Story 6 | 2026-05-30 00:00:00 | User Management | TC_USR_001 | Positive | Owner creates admin user | Owner is logged in | 1. Open Users. 2. Add user role admin. 3. Save. | Admin user is created and appears in user list. | Pending | Ricky | Manual
User Story 6 | 2026-05-30 00:00:00 | User Management | TC_USR_002 | Positive | Owner creates cashier user | Owner is logged in | 1. Add user role cashier. 2. Save. | Cashier user is created successfully. | Pending | Ricky | Manual
User Story 6 | 2026-05-30 00:00:00 | User Management | TC_USR_003 | Positive | Edit user role/status | Owner/Admin with permission is logged in | 1. Open user edit modal. 2. Update role/status. 3. Save. | User is updated and audit log records the change. | Pending | Ricky | Manual
User Story 6 | 2026-05-30 00:00:00 | User Management | TC_USR_004 | Negative | Create duplicate email user | Email already exists | 1. Add user using existing email. 2. Save. | System rejects duplicate email. | Pending | Ricky | Manual
User Story 6 | 2026-05-30 00:00:00 | User Management | TC_USR_005 | Negative | Create user with weak/blank password | Owner/Admin is logged in | 1. Leave password blank or below minimum. 2. Save. | Validation error is shown. | Pending | Ricky | Manual
User Story 6 | 2026-05-30 00:00:00 | User Management | TC_USR_006 | Negative | Cashier accesses Users page | Cashier is logged in | 1. Navigate to /users. | Role guard prevents access. | Pending | Ricky | Manual
User Story 6 | 2026-05-30 00:00:00 | User Management | TC_USR_007 | Positive | Delete/deactivate user | Target user exists | 1. Delete or deactivate target user. | User is removed/deactivated and cannot login if inactive. | Pending | Ricky | Manual
User Story 7 | 2026-05-30 00:00:00 | Location Management | TC_LOC_001 | Positive | Create parking/carwash location | Owner/Admin is logged in | 1. Open Locations. 2. Add name, address, and capacity. 3. Save. | Location is created and appears in selector/list. | Pending | Ricky | Manual
User Story 7 | 2026-05-30 00:00:00 | Location Management | TC_LOC_002 | Positive | Edit location capacity | Location exists | 1. Edit location capacity. 2. Save. | Capacity is updated and dashboard uses new value. | Pending | Ricky | Manual
User Story 7 | 2026-05-30 00:00:00 | Location Management | TC_LOC_003 | Positive | Soft delete location | Location exists and deletion allowed | 1. Delete location. 2. Confirm. | Location is removed from active list without hard delete. | Pending | Ricky | Manual
User Story 7 | 2026-05-30 00:00:00 | Location Management | TC_LOC_004 | Negative | Create location with blank name | Owner/Admin is logged in | 1. Leave name blank. 2. Save. | Validation error is displayed. | Pending | Ricky | Manual
User Story 7 | 2026-05-30 00:00:00 | Location Management | TC_LOC_005 | Negative | Create location with zero capacity | Owner/Admin is logged in | 1. Enter capacity 0. 2. Save. | System rejects invalid capacity. | Pending | Ricky | Manual
User Story 7 | 2026-05-30 00:00:00 | Location Management | TC_LOC_006 | Negative | Cashier accesses Locations page | Cashier is logged in | 1. Navigate to /locations. | Access is denied or redirected. | Pending | Ricky | Manual
User Story 8 | 2026-05-30 00:00:00 | Audit Logs | TC_AUD_001 | Positive | Login success is logged | User logs in successfully | 1. Login with valid credential. 2. Open Audit Logs as owner/admin. | Audit log contains successful login action. | Pending | Ricky | Manual
User Story 8 | 2026-05-30 00:00:00 | Audit Logs | TC_AUD_002 | Positive | CRUD action is logged | Owner/Admin performs create/update/delete | 1. Create or update sensor/user/location. 2. Open Audit Logs. | Audit log contains action, actor, table/entity, and timestamp. | Pending | Ricky | Manual
User Story 8 | 2026-05-30 00:00:00 | Audit Logs | TC_AUD_003 | Positive | Audit log filter works | Audit logs exist | 1. Filter by action/date/user if available. | Filtered results match selected criteria. | Pending | Ricky | Manual
User Story 8 | 2026-05-30 00:00:00 | Audit Logs | TC_AUD_004 | Negative | Cashier accesses audit logs | Cashier is logged in | 1. Navigate to /audit-logs. | System denies access based on role. | Pending | Ricky | Manual
User Story 9 | 2026-05-30 00:00:00 | IoT API Mock | TC_IOT_001 | Positive | Vehicle detection with valid device key | Sensor active and location matches | 1. Send POST /iot/vehicle-detection with X-DEVICE-KEY. | API creates vehicle entry and returns success. | Pending | Ricky | API
User Story 9 | 2026-05-30 00:00:00 | IoT API Mock | TC_IOT_002 | Positive | Heartbeat with valid device key | Sensor exists | 1. Send POST /iot/heartbeat with online status. | API updates sensor heartbeat/status. | Pending | Ricky | API
User Story 9 | 2026-05-30 00:00:00 | IoT API Mock | TC_IOT_003 | Negative | Vehicle detection without device key | Payload is otherwise valid | 1. Send payload without X-DEVICE-KEY. | API returns unauthorized/forbidden response. | Pending | Ricky | API
User Story 9 | 2026-05-30 00:00:00 | IoT API Mock | TC_IOT_004 | Negative | Vehicle detection with wrong device key | Payload is otherwise valid | 1. Send payload with invalid X-DEVICE-KEY. | API rejects request. | Pending | Ricky | API
User Story 9 | 2026-05-30 00:00:00 | IoT API Mock | TC_IOT_005 | Negative | Missing required device_event_id | Sensor and location valid | 1. Send payload without device_event_id. | API returns validation error. | Pending | Ricky | API
User Story 9 | 2026-05-30 00:00:00 | IoT API Mock | TC_IOT_006 | Negative | Raw distance above threshold | Sensor active with threshold configured | 1. Send raw_distance greater than threshold. | API rejects or ignores detection according to threshold rule. | Pending | Ricky | API
User Story 9 | 2026-05-30 00:00:00 | IoT API Mock | TC_IOT_007 | Negative | Sensor/location mismatch | Sensor belongs to different location | 1. Send sensor_id and location_id mismatch. | API rejects payload. | Pending | Ricky | API
User Story 9 | 2026-05-30 00:00:00 | IoT API Mock | TC_IOT_008 | Negative | Invalid heartbeat status | Sensor exists | 1. Send heartbeat with unsupported status. | API returns validation error. | Pending | Ricky | API

## Test Data
Test Data
Environment | Development / Localhost
Frontend URL | http://127.0.0.1:5173
Backend API URL | http://127.0.0.1:8000/api/v1
Owner Email | puji@carwash.test
Owner Password | puji123
Owner Role | owner
Admin Email | admin@carwash.test
Admin Password | password123
Cashier Email | cashier@carwash.test
Cashier Password | password123
Invalid Email | ghost@carwash.test
Invalid Password | wrong12345
Default Location | Rizki Car Wash
Default Sensor Code | ENTRANCE-001
Valid Device Key Header | X-DEVICE-KEY: sensor_device_secret_key
Invalid Device Key Header | X-DEVICE-KEY: wrong_key
Valid device_event_id | evt-manual-001
Duplicate device_event_id | evt-manual-001
Valid raw_distance | 20
Invalid raw_distance | 999
Valid heartbeat status | online
Invalid heartbeat status | unknown
Report Start Date | 2026-05-01
Report End Date | 2026-05-30
Invalid Report Start Date | 2026-05-30
Invalid Report End Date | 2026-05-01
New Sensor Code | ENTRANCE-TEST-001
Duplicate Sensor Code | ENTRANCE-001
New Location Name | Cabang Test QA
Invalid Location Capacity | 0
New User Email | qa.cashier@carwash.test
New User Password | password123
Restricted Role for Negative Test | cashier

## Bug
ID Bug | Bug Description | Repro Steps | Severity | Priority | ENV | Assigned to | Expected Result | Actual Result | Status
- | No confirmed bug recorded before manual execution | Run test cases first, then record confirmed defects here. | - | - | DEV | - | - | - | Pending Testing

## Test Report
Test Execution Report
System Integration Test [SIT]
Project Name | Carwash IoT System |  |  |  | QA
Phase/Sprint | Capstone Functional Testing |  |  |  | Test Coverage | 55
Timeline | Development |  |  |  | Expectation (%) | 100%
Test Date | 2026-05-30 00:00:00 |  |  |  | Actual (%) | 0%
Tester | Ricky
Execution Status
Total Test Case | Executed Test Case | Pass | Fail | Blocked | Pending | Execution Rate% | Pass Rate%
55 | 0 | 0 | 0 | 0 | 55 | 0% | 90.48%
Notes
Vehicle Entries page and physical hardware integration are deferred until hardware is ready. IoT coverage is tested through API mock requests.

## Task
Module | Feature need to be tested
Authentication & RBAC | 1. Login owner/admin/cashier 2. Logout 3. Role guard restricted pages 4. Inactive user validation
Dashboard | 1. Summary metric cards 2. Location selector 3. Empty state 4. Unauthorized access
Monitoring | 1. Sensor status list 2. Location filter 3. Valid detection update 4. Duplicate/inactive sensor rejection
Reports | 1. Summary generation 2. PDF export 3. Excel export 4. Invalid date validation 5. Role restriction
Sensor Management | 1. Create sensor 2. Edit sensor 3. Inactive status 4. Duplicate code 5. Invalid threshold
User Management | 1. Create owner/admin/cashier user 2. Edit role/status 3. Duplicate email 4. Weak password 5. Delete/deactivate user
Location Management | 1. Create location 2. Edit capacity 3. Soft delete 4. Invalid required fields
Audit Logs | 1. Login event logging 2. CRUD event logging 3. Export/filter 4. Restricted access
IoT API Mock | 1. Vehicle detection payload 2. Heartbeat payload 3. Device key validation 4. Threshold/location/duplicate validation
Analyze
Validation Unclear/Missing | Module | Type
Physical ESP32/ultrasonic hardware is not available yet; integration test should be executed after hardware is ready. | Hardware Integration | Deferred Scope
Vehicle Entries page is intentionally postponed and should be tested together with hardware flow. | Vehicle Entries | Deferred Scope
Session timeout duration needs final PRD/business decision before test acceptance. | Authentication | Open Question